## Work Plan
| Chunk 1 | Chunk 2 | Chunk 3 | Chunk 4 | Chunk 5 | Chunk 6 | Chunk 7 | Chunk 8 | Chunk 9 | Chunk 10 | Chunk 11 | Chunk 12 | Chunk 13 | Chunk 14
PHASE 0: 2020 ANCHOR YEAR — INSTANCE SEGMENTATION (COMPLETE)
Hand-trace 3,000 crown polygons across 5 training sites | bar: Chunk 1
Phase 0 Steps 1–5: discover, inspect, preprocess, DTM, tile | bar: Chunk 1
Phase 0 Step 6: 5-fold CV training (ResNet-101 U-Net, 150 epochs) | bar: Chunk 1
Phase 0 Steps 7–8: held-out evaluation + parameter sweep | bar: Chunk 1
Phase 0 Steps 9–10: full-city inference + watershed → 222k crowns | bar: Chunk 1
Phase 0 script refactor and sanity check on new pipeline | bar: Chunk 1
PHASE 1: MULTI-YEAR FEATURE EXTRACTION (18 YEARS) (COMPLETE)
Static features: building distance, water join, roof spectral scoring | bar: Chunk 1
Per-year spectral sampling (all 18 years: 2000–2024) | bar: Chunk 1
Upsample and CRS-align all non-CoE imagery to 2020 reference grid (Step 0) | bar: Chunk 1
Within-year normalisation: z-scores, percentile, NDVI-vs-roof | bar: Chunk 1
Phases 2–5: auto-labeling, stratified review, classifier training | bar: Chunk 1
PHASE 2: TEMPORAL OVERLAY QA & COVERAGE DOCUMENTATION (COMPLETE)
Temporal overlay QA: validate 2020 polygon alignment on all 18 years | bar: Chunk 2 to Chunk 3
Document training sites excluded per year (coverage gaps, land use change) | bar: Chunk 3
PHASE 3: SEMANTIC SEGMENTATION MODEL DEVELOPMENT
Build semantic segmentation head (BCEWithLogitsLoss, sigmoid activation) | bar: Chunk 2
Generate binary canopy labels from 2020 crown polygons (rasterise + dissolve) | bar: Chunk 2
Train semantic model on 2020 imagery (Phase A frozen → Phase B full) | bar: Chunk 2 to Chunk 3
Evaluate semantic model: pixel accuracy, IoU, Dice coefficient | bar: Chunk 3
Full-city semantic inference on 2020 → canopy probability raster | bar: Chunk 3
Threshold + morphological ops → 2020 binary canopy mask + polygons | bar: Chunk 3 to Chunk 4
Cross-validate 2020 instance vs semantic outputs (area agreement check) | bar: Chunk 4
◆ DECISION GATE 1: Does semantic model meet accuracy targets on 2020? Proceed / retrain / adjust architecture | bar: Chunk 4
PHASE 4: PER-YEAR FINE-TUNING — INSTANCE SEGMENTATION (9 YEARS)
Label projection: reproject 2020 polygons → generate per-crown DTM at native GSD | bar: Chunk 3 to Chunk 4
Tiling at native resolution (512×512) for each of 8 remaining instance years | bar: Chunk 3 to Chunk 4
Fine-tune: 2017, 2022, 2024 (7.5cm — highest resolution, closest to anchor) | bar: Chunk 4 to Chunk 5
Fine-tune: 2019, 2021, 2023 (14.9cm — King County recent) | bar: Chunk 5 to Chunk 6
Fine-tune: 2013, 2015 (14.9cm — oldest instance-tier, most label noise) | bar: Chunk 6 to Chunk 7
Per-year parameter sweep (DTM threshold × min distance) | bar: Chunk 5 to Chunk 7
Full-city instance inference + watershed for each of 8 years | bar: Chunk 5 to Chunk 8
Per-year evaluation: F1 by size class vs projected 2020 annotations | bar: Chunk 5 to Chunk 8
◆ DECISION GATE 2: After first 3 instance years (2017/2022/2024) — does model generalize across 7.5cm imagery? Check F1 thresholds before continuing to 14.9cm years | bar: Chunk 5
◆ DECISION GATE 3: After 14.9cm years (2019/2021/2023) — is cross-resolution transfer stable? Assess before attempting oldest years (2013/2015) with most label noise | bar: Chunk 7
PHASE 5: PER-YEAR FINE-TUNING — SEMANTIC SEGMENTATION (17 YEARS)
Label projection: rasterise binary canopy mask at each year's native GSD | bar: Chunk 4 to Chunk 5
Tiling at native resolution for all 17 remaining years | bar: Chunk 4 to Chunk 5
Fine-tune semantic models: high-res years (7.5cm + 14.9cm, 8 years) | bar: Chunk 5 to Chunk 7
Fine-tune semantic models: medium-res years (29.9cm: 2005, 2007, 2009) | bar: Chunk 7 to Chunk 8
Fine-tune semantic models: coarse years (50–60cm: 2000, 2002, 2016, etc.) | bar: Chunk 8 to Chunk 9
Full-city semantic inference + threshold → canopy mask for each year | bar: Chunk 6 to Chunk 9
Per-year validation: pixel IoU, Dice vs projected binary labels | bar: Chunk 6 to Chunk 9
Instance-semantic cross-validation for 9 dual-output years | bar: Chunk 8 to Chunk 9
◆ DECISION GATE 4: Do coarse-year semantic masks (2000, 2002, 50–60cm) meet minimum IoU? If not, exclude from temporal analysis or flag as low-confidence | bar: Chunk 9
PHASE 6: TEMPORAL CROWN LINKING
Primary anchor matching: spatial join each instance year → 2020 crowns (IoU) | bar: Chunk 8 to Chunk 9
Collect unmatched crowns from all instance years into candidate pools | bar: Chunk 9
Pre-2020 removal discovery: cluster unmatched across 2013–2019 | bar: Chunk 9 to Chunk 10
Post-2020 planting discovery: cluster unmatched across 2021–2024 | bar: Chunk 9 to Chunk 10
Build canonical crown layer (anchor + removals + plantings + lifecycle labels) | bar: Chunk 10
Project canonical layer onto all 18 semantic masks → canopy fraction per crown | bar: Chunk 10 to Chunk 11
Cross-validate temporal consistency (adjacent-year crown count agreement) | bar: Chunk 10 to Chunk 11
PHASE 7: FULL FEATURE EXTRACTION & SPECTRAL ANALYSIS
Extract spectral statistics under every canonical crown for all 18 years | bar: Chunk 10 to Chunk 11
Compute GCC = G/(R+G+B) and GRVI = (G−R)/(G+R) per crown per year | bar: Chunk 10 to Chunk 11
Compute true NDVI for 4 NIR years (2016, 2019n, 2021s, 2022n) | bar: Chunk 11
Building-relative normalisation for expanded crown set | bar: Chunk 11 to Chunk 12
Within-year z-scores and percentile ranks for full canonical set | bar: Chunk 11 to Chunk 12
Validate RGB proxy indices against true NDVI in overlapping years | bar: Chunk 12
PHASE 8: TEMPORAL ANALYSIS & DELIVERABLES
Temporal canopy change classification using active learning pipeline | bar: Chunk 11 to Chunk 13
Per-year canopy cover statistics (total area, % change from baseline) | bar: Chunk 12 to Chunk 13
Crown lifecycle analysis: removal rates, planting rates, survival curves | bar: Chunk 12 to Chunk 13
Generate final GeoPackage outputs with all temporal attributes | bar: Chunk 13
Map production: per-year canopy maps + change maps | bar: Chunk 13 to Chunk 14
Final report, methodology documentation, and data archive | bar: Chunk 13 to Chunk 14
NON-TECHNICAL MILESTONES
INTERN PROGRAM (CWU GIS INTERNSHIP)
Recruit GIS intern through CWU internship program | bar: Chunk 1
Develop training curriculum: review software, verification protocols, QA standards | bar: Chunk 1 to Chunk 2
Intern onboarding and calibration on 200-crown test set | bar: Chunk 2 to Chunk 3
Temporal overlay QA sessions: validate 2020 polygon alignment across years (with contractor) | bar: Chunk 3 to Chunk 5
Visual inspection of training sites across all 18 imagery years | bar: Chunk 4 to Chunk 6
Instance segmentation output QA: spot-check crown polygons per year | bar: Chunk 6 to Chunk 8
Semantic mask QA: visual review of canopy masks for edge cases | bar: Chunk 7 to Chunk 9
Data entry, export validation, and inconsistency flagging | bar: Chunk 9 to Chunk 11
STAKEHOLDER ENGAGEMENT & CITY COORDINATION
Kickoff briefing to CAB Board on revised pipeline and timeline | bar: Chunk 1
Participate in City tree code stakeholder group meetings (ongoing) | bar: Chunk 1
Mid-project presentation to City Planning Board (preliminary results) | bar: Chunk 7 to Chunk 8
Coordinate with City staff on data format requirements for GIS integration | bar: Chunk 8 to Chunk 9
Final presentation to City Planning Board (full results + equity analysis) | bar: Chunk 13 to Chunk 14
Community engagement: public maps and poster displays | bar: Chunk 14
EQUITY ANALYSIS & DEMOGRAPHIC OVERLAY
Acquire census block and demographic data for Edmonds | bar: Chunk 9 to Chunk 10
Acquire or compute heat vulnerability indicators by neighborhood | bar: Chunk 10
Overlay canopy change results onto demographic layers | bar: Chunk 12 to Chunk 13
Neighborhood-level equity analysis: canopy loss by demographic group | bar: Chunk 13
3-30-300 urban forestry metrics computation | bar: Chunk 13
Draft equity analysis report for city planners | bar: Chunk 13 to Chunk 14
GRANT ADMINISTRATION
Grant kickoff: finalize scope, set up financial tracking | bar: Chunk 1
Quarterly progress report #1 | bar: Chunk 4
Quarterly progress report #2 | bar: Chunk 7
Quarterly progress report #3 | bar: Chunk 10
Final grant report, financial reconciliation, compliance documentation | bar: Chunk 14
Contractor 1099 processing, insurance, accounting | bar: Chunk 1; Chunk 14
DISSEMINATION & CONFERENCE
Identify target conference (e.g., Cascadia GIS) and submission deadlines | bar: Chunk 3 to Chunk 4
Draft and submit conference abstract | bar: Chunk 8 to Chunk 9
Prepare large-format maps and poster displays | bar: Chunk 12 to Chunk 13
Conference presentation: methodology + results | bar: Chunk 13 to Chunk 14
Open-source methodology documentation and code release | bar: Chunk 13 to Chunk 14
DECISION GATES SUMMARY
DG1 (Month 4): Semantic model accuracy on 2020 — proceed / retrain / adjust? | bar: Chunk 4
DG2 (Month 5): Instance model generalizes across 7.5cm years — proceed to 14.9cm? | bar: Chunk 5
DG3 (Month 7): Cross-resolution transfer stable at 14.9cm — proceed to oldest years? | bar: Chunk 7
DG4 (Month 9): Coarse-year semantic masks meet minimum IoU — include or exclude? | bar: Chunk 9
LEGEND
Completed work (Phases 0–1) | bar: Chunk 1
Data preparation & imagery alignment | bar: Chunk 1
Semantic segmentation development | bar: Chunk 1
Instance segmentation fine-tuning (9 years) | bar: Chunk 1
Semantic segmentation fine-tuning (17 years) | bar: Chunk 1
Temporal crown linking | bar: Chunk 1
Feature extraction & spectral analysis | bar: Chunk 1
Temporal analysis & deliverables | bar: Chunk 1
Intern program (CWU) | bar: Chunk 1
Stakeholder engagement & city coordination | bar: Chunk 1
Equity analysis & demographic overlay | bar: Chunk 1
Grant administration | bar: Chunk 1
Dissemination & conference | bar: Chunk 1
Decision gate / go-no-go checkpoint | bar: Chunk 1