## Work Plan
| Chunk 1 | Chunk 2 | Chunk 3 | Chunk 4 | Chunk 5 | Chunk 6 | Chunk 7 | Chunk 8 | Chunk 9 | Chunk 10 | Chunk 11 | Chunk 12 | Chunk 13 | Chunk 14
PHASE 0: 2020 ANCHOR YEAR — INSTANCE SEGMENTATION (COMPLETE)
Hand-trace 3,000 crown polygons across 5 training sites | bar: Chunk 1
Phase 0 Steps 1–5: discover, inspect, preprocess, DTM, tile | bar: Chunk 1
Phase 0 Step 6: 5-fold CV training (ResNet-101 U-Net, 150 epochs) | bar: Chunk 1
Phase 0 Steps 7–8: held-out evaluation + parameter sweep | bar: Chunk 1
Phase 0 Steps 9–10: full-city inference + watershed → 222k crowns | bar: Chunk 1
Phase 0 script refactor and sanity check on new pipeline | bar: Chunk 1
PHASE 1: MULTI-YEAR FEATURE EXTRACTION (18 YEARS)
Static features: building distance, water join, roof spectral scoring | bar: Chunk 1
Per-year spectral sampling (all 18 years: 2000–2024) | bar: Chunk 1
Upsample and CRS-align all non-CoE imagery to 2020 reference grid (Step 0) | bar: Chunk 1
Within-year normalisation: z-scores, percentile, NDVI-vs-roof | bar: Chunk 1
Phases 2–5: auto-labeling, stratified review, classifier training | bar: Chunk 1
PHASE 2: TEMPORAL OVERLAY QA & COVERAGE DOCUMENTATION
Temporal overlay QA: validate 2020 polygon alignment on all 18 years | bar: Chunk 2 to Chunk 3
Document training sites excluded per year (coverage gaps, land use change) | bar: Chunk 3
PHASE 3: SEMANTIC SEGMENTATION MODEL DEVELOPMENT
Build semantic segmentation head (BCEWithLogitsLoss, sigmoid activation) | bar: Chunk 2
Generate binary canopy labels from 2020 crown polygons (rasterise + dissolve) | bar: Chunk 2
Train semantic model on 2020 imagery (Phase A frozen → Phase B full) | bar: Chunk 2 to Chunk 3
Evaluate semantic model: pixel accuracy, IoU, Dice coefficient | bar: Chunk 3
Full-city semantic inference on 2020 → canopy probability raster | bar: Chunk 3
Threshold + morphological ops → 2020 binary canopy mask + polygons | bar: Chunk 3 to Chunk 4
Cross-validate 2020 instance vs semantic outputs (area agreement check) | bar: Chunk 4
◆ DECISION GATE 1: Does semantic model meet accuracy targets on 2020? Proceed / retrain / adjust architecture | bar: Chunk 4
PHASE 4: PER-YEAR FINE-TUNING — SEMANTIC SEGMENTATION (17 YEARS, UNIFORM METHOD)
Temporal-anchor label transfer: approve/reject 2020 crowns vs each year at control years (2000/2020/2024); assign validity intervals | bar: Chunk 3 to Chunk 4
Region-based labels: mark non-canopy background (lawn, roof, road, water) to fix negative scarcity; review scales with temporal distance | bar: Chunk 3 to Chunk 4
Single scale-robust semantic model: blur/downsample augmentation across 7.5–60cm (no per-tier models); fine-tune from 2020 anchor | bar: Chunk 4 to Chunk 5
Full-city native-resolution inference → per-year canopy probability raster + binary mask | bar: Chunk 5 to Chunk 6
Resample all per-year masks to a common coarse grid for apples-to-apples temporal comparison | bar: Chunk 6 to Chunk 7
Threshold-independent evaluation: AUROC, average precision, best-F1 operating point per year | bar: Chunk 5 to Chunk 7
Random-point photo-interpretation (i-Tree Canopy) as resolution-agnostic validation, applied identically every year | bar: Chunk 5 to Chunk 8
Concentrate human review on oldest/coarse years (2000, 2002) and mixed-residential scenes + negatives | bar: Chunk 5 to Chunk 8
◆ DECISION GATE 2: Do per-year semantic masks pass random-point photo-interpretation (i-Tree)? Include / exclude / flag low-confidence (esp. coarse 2000/2002) | bar: Chunk 5
PHASE 5: PER-YEAR FINE-TUNING — INSTANCE SEGMENTATION (9 HIGH-RES YEARS)
Label projection: reproject 2020 polygons → per-crown DTM at native GSD (≤14.9cm years only) | bar: Chunk 4 to Chunk 5
Tiling at native resolution (512×512) for the 9 instance-tier years | bar: Chunk 4 to Chunk 5
Fine-tune: 2017, 2022, 2024 (7.5cm — highest resolution, closest to anchor) | bar: Chunk 5 to Chunk 7
Fine-tune: 2019, 2021, 2023 (14.9cm — King County recent) | bar: Chunk 7 to Chunk 8
Fine-tune: 2013, 2015 (14.9cm — oldest instance-tier, most label noise) | bar: Chunk 8 to Chunk 9
Per-year parameter sweep (DTM threshold × min distance) + full-city instance inference + watershed | bar: Chunk 6 to Chunk 9
Per-year evaluation: F1 by size class vs projected 2020 annotations | bar: Chunk 6 to Chunk 9
Instance–semantic cross-validation for the 9 dual-output years | bar: Chunk 8 to Chunk 9
◆ DECISION GATE 3: After first 3 instance years (2017/2022/2024) — does the model generalize across 7.5cm? Proceed to 14.9cm? | bar: Chunk 7
◆ DECISION GATE 4: After 14.9cm years — is cross-resolution transfer stable? Proceed to oldest years (2013/2015)? | bar: Chunk 9
PHASE 6: TEMPORAL CROWN LINKING
Primary anchor matching: spatial join each instance year → 2020 crowns (IoU) | bar: Chunk 8 to Chunk 9
Collect unmatched crowns from all instance years into candidate pools | bar: Chunk 9
Pre-2020 removal discovery: cluster unmatched across 2013–2019 | bar: Chunk 9 to Chunk 10
Post-2020 planting discovery: cluster unmatched across 2021–2024 | bar: Chunk 9 to Chunk 10
Build canonical crown layer (anchor + removals + plantings + lifecycle labels) | bar: Chunk 10
Project canonical layer onto all 18 semantic masks → canopy fraction per crown | bar: Chunk 10 to Chunk 11
Cross-validate temporal consistency (adjacent-year crown count agreement) | bar: Chunk 10 to Chunk 11
PHASE 7: FULL FEATURE EXTRACTION & SPECTRAL ANALYSIS
Extract spectral statistics under every canonical crown for all 18 years | bar: Chunk 10 to Chunk 11
Compute GCC = G/(R+G+B) and GRVI = (G−R)/(G+R) per crown per year | bar: Chunk 10 to Chunk 11
Compute true NDVI for 4 NIR years (2016, 2019n, 2021s, 2022n) | bar: Chunk 11
Building-relative normalisation for expanded crown set | bar: Chunk 11 to Chunk 12
Within-year z-scores and percentile ranks for full canonical set | bar: Chunk 11 to Chunk 12
Validate RGB proxy indices against true NDVI in overlapping years | bar: Chunk 12
PHASE 8: TEMPORAL ANALYSIS & DELIVERABLES
Temporal canopy change classification using active learning pipeline | bar: Chunk 11 to Chunk 13
Per-year canopy cover statistics (total area, % change from baseline) | bar: Chunk 12 to Chunk 13
Crown lifecycle analysis: removal rates, planting rates, survival curves | bar: Chunk 12 to Chunk 13
Generate final GeoPackage outputs with all temporal attributes | bar: Chunk 13
Map production: per-year canopy maps + change maps | bar: Chunk 13 to Chunk 14
Final report, methodology documentation, and data archive | bar: Chunk 13 to Chunk 14
NON-TECHNICAL MILESTONES
INTERN PROGRAM (CWU GIS INTERNSHIP)
Recruit GIS intern through CWU internship program | bar: Chunk 1
Develop training curriculum: review software, verification protocols, QA standards | bar: Chunk 1 to Chunk 2
Intern onboarding and calibration on 200-crown test set | bar: Chunk 2 to Chunk 3
Temporal overlay QA sessions: validate 2020 polygon alignment across years (with contractor) | bar: Chunk 3 to Chunk 5
Visual inspection of training sites across all 18 imagery years | bar: Chunk 4 to Chunk 6
Instance segmentation output QA: spot-check crown polygons per year | bar: Chunk 6 to Chunk 8
Semantic mask QA: visual review of canopy masks for edge cases | bar: Chunk 7 to Chunk 9
Data entry, export validation, and inconsistency flagging | bar: Chunk 9 to Chunk 11
STAKEHOLDER ENGAGEMENT & CITY COORDINATION
Kickoff briefing to CAB Board on revised pipeline and timeline | bar: Chunk 1
Participate in City tree code stakeholder group meetings (ongoing)
Mid-project presentation to City Planning Board (preliminary results) | bar: Chunk 7 to Chunk 8
Coordinate with City staff on data format requirements for GIS integration | bar: Chunk 8 to Chunk 9
Final presentation to City Planning Board (full results + equity analysis) | bar: Chunk 13 to Chunk 14
Community engagement: public maps and poster displays | bar: Chunk 14
EQUITY ANALYSIS & DEMOGRAPHIC OVERLAY
Acquire census block and demographic data for Edmonds | bar: Chunk 9 to Chunk 10
Acquire or compute heat vulnerability indicators by neighborhood | bar: Chunk 10
Overlay canopy change results onto demographic layers | bar: Chunk 12 to Chunk 13
Neighborhood-level equity analysis: canopy loss by demographic group | bar: Chunk 13
3-30-300 urban forestry metrics computation | bar: Chunk 13
Draft equity analysis report for city planners | bar: Chunk 13 to Chunk 14
GRANT ADMINISTRATION
Grant kickoff: finalize scope, set up financial tracking | bar: Chunk 1
Quarterly progress report #1 | bar: Chunk 4
Quarterly progress report #2 | bar: Chunk 7
Quarterly progress report #3 | bar: Chunk 10
Final grant report, financial reconciliation, compliance documentation | bar: Chunk 14
Contractor 1099 processing, insurance, accounting | bar: Chunk 1; Chunk 14
DISSEMINATION & CONFERENCE
Identify target conference (e.g., Cascadia GIS) and submission deadlines | bar: Chunk 3 to Chunk 4
Draft and submit conference abstract | bar: Chunk 8 to Chunk 9
Prepare large-format maps and poster displays | bar: Chunk 12 to Chunk 13
Conference presentation: methodology + results | bar: Chunk 13 to Chunk 14
Open-source methodology documentation and code release | bar: Chunk 13 to Chunk 14
DECISION GATES SUMMARY
DG1 (Month 4): Semantic model accuracy on 2020 — proceed / retrain / adjust? | bar: Chunk 4
DG2 (Month 5): Per-year semantic masks pass random-point validation — include / exclude / flag (esp. coarse years)? | bar: Chunk 5
DG3 (Month 7): Instance model generalizes across 7.5cm years — proceed to 14.9cm? | bar: Chunk 7
DG4 (Month 9): Cross-resolution instance transfer stable — proceed to oldest years (2013/2015)? | bar: Chunk 9
LEGEND
Completed work (Phases 0–1) | bar: Chunk 1
Data preparation & imagery alignment | bar: Chunk 1
Phase 3 — Semantic segmentation development (2020 anchor) | bar: Chunk 1
Phase 5 — Instance segmentation fine-tuning (9 years) | bar: Chunk 1
Phase 4 — Semantic segmentation fine-tuning (17 years) | bar: Chunk 1
Temporal crown linking | bar: Chunk 1
Feature extraction & spectral analysis | bar: Chunk 1
Temporal analysis & deliverables | bar: Chunk 1
Intern program (CWU) | bar: Chunk 1
Stakeholder engagement & city coordination | bar: Chunk 1
Equity analysis & demographic overlay | bar: Chunk 1
Grant administration | bar: Chunk 1
Dissemination & conference | bar: Chunk 1
Decision gate / go-no-go checkpoint | bar: Chunk 1